## Slide 1: Project Management 101
Business Management

## Slide 2: Four Basic Elements of Project Management
A successful Project Manager must simultaneously manage the four basic elements of a project:
  Resources
  Time
  Money
  Scope
All these elements are interrelated. Each must be managed effectively
All must be managed together if the project, and the project manager, is to be a success.

## Slide 3: Resources
People
Equipment
Material

## Slide 4: Time
Task durations – the time needed to complete the task
Dependencies - relationships in which tasks or milestones rely on other tasks to be performed (completely or partially) before it can be performed
Critical path - is a mathematically based algorithm for scheduling a set of project activities

## Slide 5: Critical Path cont’d
To prepare the project schedule, the project manager has to figure out what the tasks are, how long they will take, what resources they require, and in what order they should be done
If you omit a task, the project won't be completed. If you underestimate the length of time or the amount of resources required for the task, you may miss your schedule. The schedule can also be blown if you make a mistake in the sequencing of the tasks.

## Slide 6: For example:
Think of a project called "Getting Dressed In The Morning". The task "put on shirt" may have a longer duration if it is a buttoned dress shirt than if it's a pullover. It doesn't matter which order you complete the tasks "put on right shoe" and "put on left shoe", but it is important to complete the "put on pants" task before starting the "put on shoes" task.

## Slide 7
Items can be added to or removed from the critical path as circumstances change during the execution of the project
For example:
  Installation of security cameras may not be on the critical path, but if the shipment is delayed, it may become part of the critical path
  Conversely, pouring the concrete foundation may be on the critical path, but if the project manager obtains an additional crew and the pour is completed early it could come off the critical path (or reduce the length of the critical path).

## Slide 8: Money
Costs
Contingencies - Possibilities that must be prepared for
Profit
*** To maximize your chances of meeting your project budget, meet your project schedule
The most common cause of blown budgets is blown schedules

## Slide 9: Contingencies
Unusual weather or problems with suppliers are always a possibility on large projects
Companies usually include a contingency amount in the project budget to cover these kinds of things

## Slide 10: Scope
Project size
Goals
Requirements

## Slide 11: Scope cont’d
The project scope is the definition of what the project is supposed to accomplish and the budget (of time and money) that has been created to achieve these objectives
It is absolutely imperative that any change to the scope of the project have a matching change in budget, either time or resources

## Slide 12: Scope Creep
Usually, scope changes occur in the form of "scope creep". Scope creep is the piling up of small changes that by themselves are manageable, but in aggregate are significant

## Slide 13: For Example:
The project calls for a building to be 80,000 square feet in size. The client wants to add a ten foot long, 4 foot wide awning over one bay door. That's a pretty minor change. Later the client wants to extend the awing 8 feet to cover the adjacent bay. Another minor change. Then it's a change to block the upwind side to the covered area to keep out the wind. Later, it's a request to block the other end to make the addition more symmetrical. Eventually, the client asks for a ceiling under the awning, lights in the ceiling, electrical outlets, a water faucet for the workers, some sound-proofing, and a security camera. By now, the minor change has become a major addition. Make sure any requested change, no matter how small, is accompanied by approval for a change in budget or schedule or both.

## Slide 14: In the end…
You can not effectively manage the resources, time and money in a project unless you actively manage the project scope.
When you have the project scope clearly identified and associated to the timeline and budget, you can begin to manage the project resources. These include the people, equipment, and material needed to complete the project

## Slide 15: To Review
  The four basic elements of a project are:
  Resources
  Time
  Money
  Scope